## Regional Scout Plan
Regional Scout Plan
2016 - 2019

## Education for All
Youth Programme
Outcome 2019 | By 2019, the European Region will be more engaged in meeting the needs of young people of all age sections in particular regarding the spiritual development, youth empowerment and service in the community
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Design and promote a model of integrating spiritual development into a national youth programme
KPI | Define and release the model to 20 NSOs/NSAs during the Academy 2018 and distribute to all NSOs.
Actions | 1.1 Research on spiritual development in activities and programmes around Europe based also on the work undertaken by the Diversity and Inclusion Team, at World level (Duty to God Task Force) and involving Consultative Status Bodies and Spiritual Development Network (Spiritico) | bar: 2017 Q1 to 2017 Q3
1.2 design a model | bar: 2017 Q3 to 2017 Q4
1.3 Test the model also during existing events (Agora, EM Forum,) | bar: 2017 Q4 to 2018 Q4
1.4 Launch the model | bar: 2018 Q4
Objective | 2. Support NSOs/NSAs in promoting youth empowerment for young age sections (13-)
KPI | The documents on Youth Empowerment are updated with a focus on 13- age, and NSOs NSAs are supported in working in this area by a network meeting and through Roverway and Agora
Actions | 2.1 Research on youth empowerment for younger age sections in activities and programmes around Europe | bar: 2017 Q1 to 2017 Q4
2.2 Update existing documents on youth empowerment with a change of focus for younger age sections | bar: 2017 Q4 to 2018 Q4
2.3 Contribute with specific sessions to existing events (Academy, Educational Methods Forum) and a specific organise network meeting for Beaver/Cub Scouts (age range 13-) with a focus on youth empowerment | bar: 2017 Q4 to 2019 Q1
2.4 Awareness raising campaign about youth emporwerment for 13- | bar: 2019 Q1 to 2019 Q3
Objective | 3. Explore the concept of service in Scouting and promote the relevance of it as an educational tool in NSO/NSAs
KPI | 20 countries “surveyed” and a report written and presented
Actions | 3.1 Research on the understanding of the concept of service - activities and programmes around Europe | bar: 2017 Q1 to 2017 Q4
3.2 Create a grid analysis and share the results also in occasion of existing events | bar: 2018 Q1 to 2018 Q4
Objective | 4. Support the sharing of information and good practices through network meetings
KPI | Support existing networking events (Agora - 20 countries present. RoverNet-VentureNet - 15 countries) and create online opportunities involving 70% of NSO's.
Actions | 4.1 Organise Agora | bar: 2018 Q1 to 2018 Q2; 2019 Q1 to 2019 Q2
4.2 Organise RoverNet / VentureNet | bar: 2018 Q3 to 2018 Q4
4.3 Organise the European Scout Educational Forum | bar: 2018 Q1 to 2018 Q2
4.4 Faciltate long distance networking exploring a better use of on-line tools
4.5 Keep supporting existing and new networks related to Educational Methods created by NSOs/NSAs or othe relevant stakeholders (Sea Scout Network, Center Manager Conference,...)
Skills for life
Outcome 2019 | By 2019, the European Region will have adapted world polices, achieved better recognition of training and volunteer management; and the increased use of new technologies
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Explore the different existing technologies that are currently used in the field of education, and showcase existing experiences at Regional and National level that involve the usage of new technologies applied to training and programme
KPI 1 | Provide 5 case study to present to the Region and show 10 different new technology tools that can be analysed and compared
Actions | 1.1 Collect and study tools from the educational sector | bar: 2017 Q1 to 2017 Q4
1.2 Collect existing experiences from NSO/NSA of using new technologies to deliver programme and training | bar: 2017 Q2 to 2017 Q4
1.3 Explore if/how NSO/NSAs use social media as an educational tool | bar: 2017 Q3 to 2018 Q1
1.4 Conduct a quality assurance and impact assesment of these experiences | bar: 2017 Q3 to 2018 Q1
1.5 Prepare an infograph, document or video to share the benefit of using new technologies based in the experiences gathered and the analisys performed | bar: 2018 Q2 to 2018 Q3
1.6 Establish cooperation and seek support and involvement from I/O Network
Objective | 2. Increase, at Regional and National level, the level of expertise in developing new ways to deliver Training and Youth programme and in how to adapt educational content using new techonologies.
KPI 1 | Provide 2 Training opportunitties for the Region and the NSO/NSA
Actions | 2.1 Explore the concept of Gamification and storytelling | bar: 2018 Q1 to 2018 Q3
2.2 Organise workshops or training opportunities on the use of new technologies in NSO/NSA with particular focus on social media, gamification, storytelling, etc. | bar: 2018 Q4; 2019 Q2
Objective | 3. Make policies known for the relevant people in the Region and the NSO/NSAs, highlight the benefits of their implementation and offer tailored support for their adaptation.
KPI | Provide at least 4 opportunities to get to know the world policies more in depth, targeted for the relevant audience , and provide support for the NSO/NSAs requesting it
Actions | 3.1 Get acquainted with the policies | bar: 2017 Q1
3.2 Participate in the Implementing World Policies Workshop | bar: 2017 Q2
3.3 Explore other region's actions and campaigns about the topic | bar: 2017 Q2 to 2017 Q3
3.4 Design a toolkit for implementation of the World Policies | bar: 2017 Q2 to 2018 Q2
3.5 Deliver workshops in how to use the toolkit | bar: 2017 Q4; 2018 Q2; 2018 Q4; 2019 Q2
3.6 Offer tailored support in the process of revising national policies based on the relevant world policies | bar: 2018 Q1 to 2019 Q4
Objective | 4. Provide support for NSO/NSA in implementing existing methodologies and tools for self-recognition
KPI | Showcase at least 10 tools used in the field of recognition of competencies
Actions | 4.1 Gather tools and methods from within the movement and externally | bar: 2017 Q2 to 2017 Q3
4.2 Analyse tools (what has worked for who) - pros and cons of each. | bar: 2017 Q4 to 2018 Q2
4.3 Showcase the results | bar: 2018 Q2 to 2018 Q4
4.4 Provide support for the NSO/NSAs requesting it | bar: 2018 Q2 to 2019 Q4
Objective | 5. Create guidelines on how to develop validation/internal recognition policy in the NSO/NSA and facilitate further training and support to equip them with the skills needed for developing a policy
KPI | Create guidelines/toolkit and spread the tool
Actions | 5.1 Consult with experts on how to develop an internal recognition policy | bar: 2017 Q3 to 2017 Q4
5.2 Create guidelines | bar: 2018 Q1 to 2018 Q3
5.3 Disseminate the results to the relevant people in the NSO/NSAs | bar: 2018 Q4; 2019 Q2
5.4 Offer further tailored support if needed | bar: 2018 Q2 to 2019 Q4
Objective | Facilitate networking between the relevant actors in the NSO/NSAs by strenghten the network through continous dialouge and explore other ways to benefit from the shared knowledge
KPI | Organising at least 7 networking opportunities for the MOVIS network with a designated person from at least 30 NSAs
Actions | 6.1 Identify the relevant people in associations and create a list | bar: 2017 Q1 to 2017 Q3
6.2 Organise the MOVIS network meeting in 2017 and 2019 keeping record of the knowledge and tools collected, on the online platform | bar: 2017 Q4; 2019 Q2
6.3 Organise at least 3 webinars/on-line discussions on relevant challenges addressed by the network | bar: 2018 Q1; 2018 Q3; 2019 Q1
6.4 Facilitate at least 3 networking opportunities at existing international events for interested people working at national level (e.g. Academy and EM Forum) | bar: 2018 Q2; 2018 Q4; 2019 Q3
Diversity and Inclusion
Outcome 2019 | By 2019, the European Region will increasingly reflect the rich diversity of the communities across Europe by being more welcoming
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Creating the environment to connect different actors and networks active in the field of diversity and inclusion to enable better exchange, the increase of their range of impact and the strengthening of the expertise within the European Scout Region.
KPI 1 | A stable relation with the consultatives status bodies related to spiritual development (Spiriteco, European Interreligious Forum ) and diversity and inclusion (Overture Network) is established and support is given so they are able to strengthen their networks, which enables them to consolidate their work and expertise (and enables support towards NSOs/NSAs)
Actions | 1.1 Organize at least a joint event between the consultative status bodies with religious/spiritual focus active in Europe and the spiritual development network (Spiriteco) to stimulate collaboration and to improve their support towards NSO/NSAs. *In collaboration with the Youth Programme Team | bar: 2017 Q1 to 2017 Q4
1.2 Include in the work of the European Scout Region and support the strengthening of the spiritual development network (Spiriteco); support the consolidation of the EIF as a valuable resource platform for NSOS/NSAs | bar: 2017 Q1 to 2018 Q3
1.3 Support collaboration between Overture Network, WAGGS and WOSM in order to broaden the Overture Network reach and to preserve the expertise and knowledge they have and are building up. | bar: 2017 Q3; 2018 Q1 to 2019 Q4
Objective | 2. Develop a model which will enable the NSO/NSAs to implement (embed) or re-assess (re-evaluate) diversity and inclusion in the DNA in their organisation.
KPI 1 | A Diversity and Inclusion implementation/assessment model is available within 1 year and implemented by at least 15 organisations by the end of the triennium and of whom 10 are being supported to (3 KPI)
Actions | 2.1 Design the model (not best practices, more an Organisational Development like model) | bar: 2017 Q1 to 2017 Q4
2.2 Deliver the model (training of the NSO/NSAs and on training events (Academy, Educational Forum) in collaboration with Global Support. | bar: 2018 Q1 to 2018 Q4
2.3 Provide specific tailored support on mainistreaming diversity and inclusion in particular throuh a specific LTF project
Objective | 3. Support NSA/NSOs in developing longterm sustainable solutions to welcome newcommers.
KPI 1 | 10 NSO/NSAs have developed solutions to welcome newcommers by having leaders who are trained in facilating Peace Dialogues, by learning from others and by using toolkits(s) and materials made available by the Region in collaboration with external experts/organistions.
Actions | 3.1 Training of trainers (for different NSOs/NSAs) as Peace educators in order to actively promote interreligious and intercultural dialogue by training leaders in their own NSO/NSA. (CoE Workplan 2017) | bar: 2017 Q1 to 2018 Q2
3.2 Support training development and make results available to NSAs/NSOs (*Erasums Plus project: Time to be welcome) | bar: 2017 Q1 to 2018 Q4
3.3 Collect and share best practices of the projects supported through different funding channels | bar: 2018 Q1 to 2018 Q4
3.4 Bring the NSOs/NSAs, regarding refugees and migrants, together with external experts to exchange expertise and delevelop or adjust a (existing) tool kit regarding refugees (eg. Including psychological First Aid kit) | bar: 2017 Q3; 2018 Q1 to 2019 Q4
3.5 Develop short and accesible Info template leaflet/brochures regarding reaching out to deprived/disadvantage childrens | bar: 2018 Q4 to 2019 Q4
Objective | 4. Increase the visibility of Diversity and Inclusion, in all its aspects, in the European scout region in order to increase the overall awareness.
KPI 1 | Diversity and Inclusion topics are represented on international events, and on social media and diversity and inclusion information is easily accessable by the NSOs and NSAs.
Actions | 4.1 Be present at international events and facilitate workshop on international events, like Roverway, The Academy, Educational Forum, local Jamborees, ...
4.2 Contribute to the development of a Knowledge sharing platform (in the frame of Scout.org or Euro.Scout.Info) and collect Diversity and Inclusion related content for this platform.
4.3 Organize a D&I event which includes experts from the NSOs/NSAs and the networks (incl. Participants of previous activities), with the aim of identifying gaps and give guidance regarding the Diversity and Inclusion in order to be able to maximaze the regions contribution to the realization of Mission 2023. (Consolidation event) | bar: 2019 Q1 to 2019 Q4
4.3 Keep the D&I layout and the awarness campaign (eg. via social media), which can be used and adapted by the NSO/NSAs.
Social Impact
Outcome 2019 | By 2019, the European Region will have increased the number of community impact projects and the capacity to measure them
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 2. Members of the European Region will have a mutual and clear understanding of the meaning of Social Impact, and will therefore feel comfortable in championing this within individual NSO/NSAs.
KPI 1 | At least one third of NSO/NSAs will have a robust understanding Social Impact and the agreed key messages of Social Impact to be present at all relevant major events and embedded within projects across the Region.
Actions | 1.1 Gathering of information in order to analyse the current awareness/understanding of social impact | bar: 2017 Q1 to 2017 Q3
1.2 Provide NSO/NSAs the opportunity to learn about SI via exploratory sessions throughout the triennium period at events such as (Academy, Agora etc) | bar: 2017 Q4 to 2018 Q4
1.3 Work in partnership with other teams within the wider Education for All team and link up at relevant events to showcase Social Impact.
1.4 Work with the External Representatives & Communications Team to ensure our social impact as a region is championed as a key message throughout.
1.5 Ensure Social Impact is a key theme for all appropriate Regional Events | bar: 2018 Q4 to 2019 Q4
1.6 Create a study of how social impact can be increased | bar: 2018 Q4 to 2019 Q1
1.7 Headline event to showcase results | bar: 2019 Q2
Objective | 2. The European Region will have a understanding of measuring impact in terms of both scale and effect.
KPI 1 | 25% of NSO/NSAs will have used or will have plans to use the measurement tool developed by the World Level and understand how the tool can be used to used to their advantage
Actions | 2.1 We will work with WOSM & the Regional office to understand the tool on its launch. | bar: 2017 Q1 to 2017 Q4
2.2 The team will Champion and explain the tool & events and through communications & at events | bar: 2017 Q3 to 2018 Q3
2.3 Support the piloting and implementation | bar: 2017 Q3 to 2019 Q3
2.4 Explore alternative methods of measuring SI (on going) | bar: 2017 Q1 to 2019 Q2
2.5 Measure the impact of the region | bar: 2019 Q1 to 2019 Q4
2.6 Work with Messengers of Peace to identify common aims and learn about measurement process already in place | bar: 2017 Q1 to 2017 Q4
2.7 Identify top awards and initiatives with Social Impact involved as examples to show ways to measuring social impact | bar: 2019 Q1 to 2019 Q2
Note on A37: This is not measurable. Anyway I think they should provide support to us, not us to them. I would directly erase this KPI -Raül Molina

## Strengthening our Organisation
Tailored Support
Outcome 2019 | By 2019, there will be a significant increase in the quality of Scouting undertaken in the European Region
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Continuously improve the quality of Tailored Support provided to NSO/NSAs
Objective | 2. Make NSO/NSAs aware of the benefits of Tailored Support for their organisations
Objective | 3. Provde resources for NSO/NSAs to support them in their organisational development efforts amd their strategic management
KPI | 90% of all tailored support engagements are evaluated either good or very good by the receiving NSO/NSAs and 15% of all Tailored Support engagements are NSO/NSA to NSO/NSA support
Actions | 1.1 Introduce an update to the TS concept including new, innovative methods of delivery | bar: 2017 Q1 to 2017 Q4
1.2 Run awareness raising campaign for TS with the Communications Team | bar: 2017 Q3 to 2018 Q1
1.3 Support regional volunteers, including ESC, to act as ambassadors for TS
1.4 Provide and utilise a user-friendly way of evaluating TS engagements | bar: 2017 Q4; 2018 Q4; 2019 Q4
1.5 Provide an annual summary of evaluation results and revise TS concept accoordingly
1.6 Prepare an induction training for new consultants and apply it | bar: 2017 Q2 to 2017 Q4
1.7 Provide a support system for consultants
1.8 Use GSAT results, committee contacts etc. in an integrated way to match NSO/NSAs | bar: 2017 Q1 to 2017 Q3
1.9 With the world level, introduce the GS Web Platform to the Region and NSO/NSAs | bar: 2017 Q2 to 2017 Q4
1.10 Finalise and further develop the induction training for new board members and regularly apply it | bar: 2017 Q1 to 2017 Q3
1.11 Implement an information campaign on what the indiuction training is about and how it works | bar: 2017 Q4 to 2018 Q2
1.12 Regularly apply the induction training and monitor follow-up with NSO/NSAs
1.13 Create online supporting diocuments for all items of the OD Model
1.14 Run workshops at The Academy | bar: 2017 Q4; 2018 Q4; 2019 Q4
Growth
Outcome 2019 | By 2019, there will be significant increase in the number of members in the European Region
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Suppoort NSO/NSAs to sustainably increase membership by developing a sustainable, long term Growth Strategy
KPI | At least 20 NSO/NSAs use a strategic approach to Growth and have developed a growth strategy
Actions | 1.1 Deliver a mapping of existing work on membership growth strategies in NSO/NSAs | bar: 2017 Q1 to 2017 Q4
1.2 Use the result of the mapping, deliver a support platform focussing on growth for NSO/NSAs | bar: 2017 Q3 to 2018 Q2
1.3 Run workshops at The Academy | bar: 2017 Q4; 2018 Q4; 2019 Q4
GSAT
Outcome 2019 | By 2019, the organisational health of 90% of the associations that have undergone GSAT will be improved in the areas of weakness identified and addressed through direct support
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Ensure NSO/NSAs and the Region have a clear understanding of their oprganisational capacities
Objective | 2. Use GSAT as a starting pointto improve organsational development
KPI | 90% of the GSAT assessments are transferred into a concrete action plan and/or concrete support to the NSO/NSA
Actions | 1.1 Use diverse communication channels to actively promote the use of GSAT, with Communicatons Team
1.2 Analyse date from GSAT to identify opportunities for TS and training | bar: 2017 Q1; 2018 Q4
1.3 Use GSAT assessments to identify and share best practices
1.4 Develop methods and actively support NSO/NSAs in conducting self-assessments | bar: 2017 Q3; 2018 Q1 to 2018 Q3
1.5 Review, revise and implement improvements to the GSAT follow-up process | bar: 2017 Q1 to 2017 Q3

## Spreading our Message
External Relations & Funding
Outcome 2019 | By 2019, the European Region will be using effective tools to strengthen the position of Scouting as the leading educational youth organisation in Europe
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. NSO/NSAs are actively shaping national and European youth policy
KPI | 25 NSO/NSAs participating in capacity building events for External Relations
Actions | 1.1 Capacity building events for NSO/NSAs external representatives - Network meeting | bar: 2017 Q4; 2018 Q4; 2019 Q4
1.2 GSAT improvement - evidence to prove successful External Relations in NSO/NSAs | bar: 2017 Q1; 2018 Q1; 2019 Q1
1.3 Map current situation of external relations in NSO/NSAs | bar: 2017 Q4; 2019 Q2
1.4 Follow NSO/NSA needs through GSAT evaluations and Tailored Support requests | bar: 2017 Q1; 2017 Q3; 2018 Q1; 2018 Q3; 2019 Q1; 2019 Q3
1.5 Capacity building in ER for NSO/NSAs - strategy, structuring, through e.g. Academy | bar: 2017 Q2 to 2017 Q4; 2018 Q4; 2019 Q3
1.6 Collect and share best practices of advocacy among NSO/NSAs | bar: 2017 Q4; 2018 Q4; 2019 Q3
Objective | 2. WSR constantly improves its external relations and advocacy
KPI | 2 reviews and recommendations on ESR external relations improvement
Actions | 2.1 Evaluation of the ESR advocacy/external relations | bar: 2017 Q4; 2018 Q4; 2019 Q4
2.2 Recmmendatins on improvements | bar: 2017 Q4; 2018 Q4; 2019 Q4
Objective | 3. ESR and NSO/NSA collaborate on common advocacy goals
KPI | 6 policy position briefings provided for NSO/NSAs
Actions | 3.1 ESR position briefings to NSO/NSA representatives on most relevant European processes | bar: 2017 Q1 to 2019 Q1
Objective | 4. NSO/NSAs constantly strengthen sustainability of their funding systems
KPI | 12 NSO/NSAs participate in capacity building events
Actions | 4.1 Capacity building on sustainable funding | bar: 2018 Q2; 2019 Q2
4.2 Project application reviews | bar: 2017 Q1 to 2017 Q2; 2017 Q4 to 2018 Q2; 2018 Q4 to 2019 Q2; 2019 Q4
4.3 Mapping current situation and needs in NSO/NSAs | bar: 2017 Q4; 2019 Q2
4.4 Follow NSO/NSA needs through GSAT and applications for tailored support | bar: 2017 Q1; 2017 Q3; 2018 Q1; 2018 Q3; 2019 Q1; 2019 Q3
Objective | 5. NSO/NSAs are constantly informed about existing funding opportunities in Europe
KPI | 12 information sets on funding opportunities are provided for NSO/NSAs
Actions | 1.1 Newsletter on finding opportunities at European level
1.2 Provide knowledge and raising awarenness among NSO/NSAs of fundraising opportunities (Academy) | bar: 2017 Q1 to 2017 Q3; 2018 Q3; 2019 Q3
1.3 Collect and share best practices of fundraising among NSO/NSAs | bar: 2017 Q2; 2018 Q1; 2018 Q4; 2019 Q2
Communications
Outcome 2019 | By 2019, the European Region will be communicating better internally and externally according to feedback from the NSOs and partners
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Use up to date methods of communications in a precise, clear and transparent way
KPI | A renewed system of communication is established and implemented
Actions | 1.1 Development - provisional changes to the communication channels in the Region | bar: 2017 Q2 to 2017 Q3
1.2 Assessment of the current methods of communication in use | bar: 2017 Q4 to 2018 Q1
1.3 Development of a new communication system for the Region | bar: 2018 Q2 to 2018 Q3
1.4 Implementation of the new communicatiion system of the Region | bar: 2018 Q4 to 2019 Q1
1.5 Setting rules for usage of the European Scout Region graphics | bar: 2017 Q2
1.6 Renew - Create Social Media guidelines for the Region including focus on External Representation and update | bar: 2017 Q2; 2018 Q3
1.7 Implement the Social Media Guidelines for the Region, including focus on External Representation | bar: 2017 Q3 to 2017 Q4; 2018 Q4 to 2019 Q1
1.8 Create a calendar for content to be published on Regional social media | bar: 2017 Q2
1.9 Enhance - Create communication guidelines for event planning teams | bar: 2017 Q2
1.10 Implement guidelines for event planning teams | bar: 2017 Q3
1.11 Introduction - Create a storage location for documents of the volunteer working groups of the Region | bar: 2018 Q3 to 2018 Q4
1.12 Create guidelines for the transfer of knowledge in between triennia | bar: 2019 Q1
1.13 Create a storage system for the Region | bar: 2019 Q1
Objective | 2. Support NOS/NSAs in improving their public iimage and assist in developingand implementing communication strategies
KPI | 75% of the NSAs will have benefitted from at least 1 of the different opportiunities offered - events, training, webinars
Actions | 1.1 Communication event - Assess the needs of NSO/NSAs relevant for the event | bar: 2017 Q3 to 2018 Q1
1.2 Organise an event on how to imoprove the public image of Scouting in society | bar: 2018 Q2
1.3 Spread the outputs of the event | bar: 2018 Q3 to 2018 Q4
1.4 Strategies - publish a manual on how to create a communications strategy | bar: 2018 Q4
1.5 Offer training sessions on strategies at specific events | bar: 2017 Q4; 2018 Q4; 2019 Q2; 2019 Q4
1.6 Topic training - run webinars | bar: 2017 Q4; 2018 Q3; 2019 Q3
1.7 Run sessions at regional events | bar: 2017 Q4; 2018 Q4; 2019 Q2; 2019 Q4
1.8 Young Spokesperson training in 2017 | bar: 2017 Q1 to 2017 Q2
1.9 Exchanges - Identify good stories by NSO/NSAs than can be replicated in other contexts
1.10 Create a Facebook group for NSO/NSA Comms people | bar: 2017 Q1 to 2017 Q2
1.11 Organise a network meeting for Comms in 2019 | bar: 2019 Q1
1.12 Collect and disseminate best practices from NSO/NSAs

## Continuous Improvement
Working Methods
Outcome 2019 | By 2019, an effective Regional Scout Plan 2019-2021 will be in place following rich contributions from the entire Region
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Develop a process to ensure a transparent regional plan which has had rich contributions from NSO/NSAs
KPI | An effective Regional Scout Plan is delivered - measured at the time we elaborate the plan after the conference and by condiucting a gut reaction survey
Actions | 1.1 Establish the processes used in previous triennia by interviewing those involved | bar: 2017 Q1
1.2 Identify key earnings from the previous proocess | bar: 2017 Q2
1.3 Research innovative ways and existing best practice ihn creating a user-friendly process | bar: 2017 Q2 to 2017 Q3
1.4 Create a draft process including a timeline | bar: 2017 Q3
1.5 Consult staeholders (NSO/NSAs, ESC, Regional Volunteers, Staff) on the process | bar: 2017 Q4
1.6 Gain committee approval of the process | bar: 2018 Q1
Objective | 2. Ensure the establishment of a team responsible for drafting the Regional Scout Plan
Actions | 2.1 Draft terms of reference and member profiles for the Regional Scout Plan Team to be approved by ESC | bar: 2017 Q4 to 2018 Q1
2.2 Collaborate with VM Team to establish and execute a recruitment process | bar: 2017 Q4 to 2018 Q2
2.3 Gain ESC approval of the proposed appointees | bar: 2017 Q4 to 2018 Q2
2.4 Brief the Triennial Plan drafting team on its task | bar: 2018 Q2
Objective | 3. Track and monitor the creation of the Regional Scout Plan
Actions | 3.1 Monitor the process against key deadlines and TOR | bar: 2018 Q3 to 2019 Q4
Objective | 4. Evaluate the process and its outcomes, ensuring the required changes are made
Actions | 4.1 Identify ownership of the process and its evaluation going forward | bar: 2019 Q2 to 2019 Q4
4.2 Develop a method to evaluate the drafting process of the Regional Scout Plan and ensure the process can be repeated for future plans | bar: 2019 Q2 to 2019 Q4
4.3 Standardise the approach to ensure it can be reused in the future | bar: 2019 Q2 to 2019 Q4
Objective | 5. Consolidate the process and the changes to ensure a repeatable system that will be received by the new ESC (2019-2012) and adopted moving forward
Actions | 5.1 Standardise the approach to ensure it can be reused in the future | bar: 2019 Q3 to 2019 Q4
5.2 Develop a method to evaluate the drafting process of the Regional Scout Plan and ensure the process can be repeated for future plans | bar: 2019 Q3 to 2019 Q4
Outcome 2019 | By 2019, there will be an accepted governance model for the Region, recognising the political responsibilities of the ESC, but accepting the devolving of practical responsibilities to the NSO/NSAs through their participations n the working groups of the Region
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Carry out a consultation to map and analyse expectations and potential contributions of NSO/NSAs and key stakeholders
KPI | There are effective measures in place to ensure a sustainable governance model for the Region, measured by validating the proposals with focus groups
Actions | 1.1 Identify the current ways of working and the history of developments in this area of work in the Region | bar: 2017 Q1 to 2017 Q2
1.2 Explore best practice models through consultation with NSO/NSAs and relevant and similar organisations or institutions | bar: 2017 Q2 to 2017 Q3
1.3 Analyse possible solutions for increased efficiency with guidance from ESC and staff | bar: 2017 Q3 to 2017 Q4
1.4 Develop recommendations to address identified challenges of the Region and gain approval from the ESC | bar: 2017 Q4
Objective | 2. Ensure the implementation of the proposals identified by the mapping and analysis along with communication with NSO/NSAs
Actions | 2.1 Develop a plan of implementation for the recommendations, including responsibilities, ownership and roles | bar: 2018 Q1
2.2 Assign areas of responsibility to relevant parties | bar: 2018 Q1
2.3 Provide clear update to NSO/NSAs communicating the proposed changes | bar: 2018 Q1 to 2018 Q2
Objective | 3. Reinforce, monitor and evaluate the proposals made to maintain and further develop the progress achieved
Actions | 3.1 Conduct an evaluation of the implementation of changes from different perspectives - volunteers, ESC, staff | bar: 2019 Q1 to 2019 Q2
3.2 Monitor and follow-up on ways forward for the process, consulting the VM Team, the ESC and general evaluations | bar: 2018 Q3 to 2019 Q4
3.3 Develop guidelines for the processes for the future, icluding handover to the next committee | bar: 2019 Q4
Actions | 3.4 Evaluate the progress of continuous improvement from an NSO/NSA perspective | bar: 2019 Q3
Objective | 4. Consolidate the process and the changes to ensure a repeatable system will be received by the new ESC - 2019-2021 - and adapted moving forward
Actions | 4.1 Standardise the approach to ensure it can be reused in the future | bar: 2019 Q3 to 2019 Q4
4.2 Submikt to the new ESC - 2019-2021 | bar: 2019 Q3 to 2019 Q4
Volunteer Management
Outcome 2019 | By 2019, the Region volunteers will be happy and effective in delivering the Regional Scout Plan
|  | 2017 |  |  |  | 2018 |  |  |  | 2019
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Objective | 1. Provide support to ESC and volunteers in the recruitment of volunteers by designing a provess based on the MOVIS framework
KPI | That 75% of volunteers will be satisfied as identified in their annual performance review - measure quantified or qualified by anecdota evidence
Actions | 1.1 Gather internal information from volunteers, coordinators, ESC | bar: 2017 Q3 to 2017 Q4
1.2 Gather external informatiom from coordinators, teams ad ESC - SWOT analysis, best practices | bar: 2018 Q2
1.3 Draft a recruitment process to support the Region in recruiting and engaging - Research innovative ways and existing best practice ihn creating a user-friendly process | bar: 2018 Q3
1.4 Provide training and implementation | bar: 2019 Q1
Objective | 2. Review and consolidate the performance review mechanism for the ESC and its voklunteers
Actions | 2.1 Identify personal and developmental goals | bar: 2017 Q2 to 2017 Q4
2.2 Implement the agreed goals for volunteers | bar: 2017 Q4
2.3 Evaluate the goals and performance | bar: 2018 Q2
Objective | 3. Continue and consolidate the succession planning process to facilitate transition periods
Actions | 3.1 Identify the areas of succession | bar: 2018 Q1
3.2 Design a process for the agreed areas of succession | bar: 2018 Q3
3.3 Raise the importance of documenting the work from the teams and committee | bar: 2019 Q2